## Time track
| Hao (ScMa) | Nina | Joonas | Erika | Sofia | Kaarlo | Tuomo | Binh | Heidi
Sprint 0
16.10. - 22.10. | 6 | 5 | 3 | 3 | 3 | 2 | 3 | 5 | 5
23.10. - 29.10. | 7 | 11 | 4 | 4 | 4 | 4 | 4 | 5 | 5
30.10. - 05.11. | 15 | 2 | 2 | 2 | 1 | 2 | 2 | 10 | 9
Total | 28 | 18 | 9 | 9 | 8 | 8 | 9 | 20 | 19
Remaining | -8 | 12 | 21 | 21 | 22 | 22 | 21 | 10 | 11
Sprint 1
06.11 - 12.11. | 8 | 6 | 10 | 3 | 3 | 10 | 2 | 4 | 4
13.11. - 19.11. | 5 | 6 | 12 | 8 | 4 | 8 | 8 | 0 | 9
20.11. - 26.11. | 7 | 16 | 12 | 10 | 9 | 7 | 3 | 0 | 12
Total | 20 | 28 | 34 | 21 | 16 | 25 | 13 | 4 | 25
Remaining | -7 | 14 | 17 | 30 | 36 | 27 | 38 | 36 | 16
Sprint 2
27.11 - 03.12. | 8 |  | 8 | 4 | 4 | 13 | 4 | 2 | 11
04.12. - 10.12. | 1 |  | 2 |  | 3 |  |  | 2 | 8
11.12. - 17.12. | 4 |  |  | 2 | 3 |  |  | 2 | 8
18.12. - 24.12. | 3 |  | 2 | 3 | 3 | 6 | 4 | 2 | 8
25.12. - 31.12. |  |  | 11 | 2 | 2 | 20 | 14 | 2 | 3
1.1. - 7.1. |  |  | 14 | 6 | 4 | 12 | 10 | 0 | 6
8.1 - 14.1 |  | 9 | 26 | 2 | 6 | 14 | 10 | 18 | 10
15.1 - 21.1. | 10 | 23 | 22.5 | 7 | 9 | 15 | 12 | 24 | 4
Total | 26 | 32 | 85.5 | 26 | 34 | 80 | 54 | 52 | 58
Remaining | -12 | 22 | -28.5 | 44 | 42 | -13 | 24 | 24 | -2
Sprint 3
22.1 - 28.1. | 3 | 25 | 3 | 11 | 13 | 21 | 8 | 2 | 18
29.1 - 4.2 | 7 | 35 | 17 | 16 | 16 | 14 | 14 | 8 | 22
Total | 10 | 60 | 20 | 27 | 29 | 35 | 22 | 10 | 40
Remaining | -1 | 2 | -8.5 | 57 | 53 | -8 | 42 | 54 | -2
Sprint 4
5.2 - 11.2 | 2 | 32 | 12 | 18 | 21 | 20 | 25 | 6 | 11
12.2 - 18.2 | 8 | 23 | 7 | 13 | 12 | 11 | 6 | 18 | 12
Total | 10 | 55 | 19 | 31 | 33 | 31 | 31 | 24 | 26
Remaining | 10 | -13 | 12.5 | 66 | 60 | 1 | 51 | 70 | 12
Sprint 5
19.2 - 25.2 |  | 3 |  | 4 | 5 | 15 | 1 | 3 | 10
26.2 - 3.3 | 7 | 53.5 | 16.5 | 11 | 7 | 29.5 | 22 | 17.5 | 5 | Binh owns note: 1.5 hour meeting 22.02 8 hours (28/02/2022), 8 hours (29/02/2022)
4.3 - 10.3 | 14 | 14 | 16 | 15 | 14 | 6 | 18 | 3 | 10 |  | 3 hour Sprint Meeting
Total | 21 | 70.5 | 32.5 | 30 | 26 | 50.5 | 41 | 23.5 | 28
Remaining | 10 | -38.5 | 25 | 81 | 79 | -4.5 | 55 | 91.5 | 29
Sprint 6
11.3 - 17.3 | 4 |  | 3 | 13 | 15 | 0.5 | 10 | 6.5 | 22 | Binh owns note: Progress and Daily Thursday (14/03/2024) - 1.5 hours
18.3 - 24.3 | 13 | 7 | 2 | 18 | 21 | 16 | 13 | 8 | 4 |  | Documentation on ML and rereading Nina's code: 5 hours (14/03/2024)
Total | 17 | 7 | 5 | 31 | 36 | 16.5 | 23 | 14.5 | 26 |  | 3 hours on Sprint Meeting
Remaining | -7 | -45.5 | 20 | 50 | 43 | -21 | 32 | 77 | 6 |  | 5 hours on 18/03/2024
Sprint 7
25.3 - 31.3 | 2 |  |  | 4 | 5 |  | 12 | 0 |  | Planned by Binh
1.4 - 7.4 | 3 | 8 | 7 | 14 | 5 | 9 | 8 | 5 |  | 11 hours 11/04/2024 | completed
8.4 - 14.4 | 8 | 6 | 7.5 | 18 | 17 | 3 | 20 | 21 |  | 11 hours 12/04/2024 | completed
15.4 - 8.5 (after Sprint 7 ends) | 7 | 8 | 3 | 14 | 16 | 3 | 3 | 51 | 3
Total | 20 | 22 | 17.5 | 50 | 43 | 15 | 43 | 77 | 3 | 11 hours 20/04/2024 | completed
Remaining | -27 | -67.5 | 2.5 | 0 | 0 | -36 | -11 | 0 | 0 | 11 hours 21/04/2024 | completed
[10 empty] | 11 hours 22/04/2024 | completed
| Hao (ScMa) | Nina | Joonas | Erika | Sofia | Kaarlo | Tuomo | Binh | Heidi | 11 hours 23/04/2024 | completed
Total planned | 125 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 11 hours 24/04/2024 | completed
Total done | 152 | 292.5 | 222.5 | 225 | 225 | 261 | 236 | 225 | 225
Sprint 0 (done) | 28 | 18 | 9 | 9 | 8 | 8 | 9 | 20 | 19
Sprint 1 (done) | 20 | 28 | 34 | 21 | 16 | 25 | 13 | 4 | 25
Sprint 2 (done) | 26 | 32 | 85.5 | 26 | 34 | 80 | 54 | 52 | 58
Sprint 3 (done) | 10 | 60 | 20 | 27 | 29 | 35 | 22 | 10 | 40
Sprint 4 (done) | 10 | 55 | 19 | 31 | 33 | 31 | 31 | 24 | 26
Sprint 5 (done) | 21 | 70.5 | 32.5 | 30 | 26 | 50.5 | 41 | 23.5 | 28
Sprint 6 (done) | 17 | 7 | 5 | 31 | 36 | 16.5 | 23 | 14.5 | 26
Sprint 7 (done) | 20 | 22 | 17.5 | 50 | 43 | 15 | 43 | 77 | 3
Sprint 0 (plan) | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Sprint 1 (plan) | 41 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Sprint 2 (plan) | 62 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Sprint 3 (plan) | 83 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
Sprint 4 (plan) | 104 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
Sprint 5 (plan) | 125 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225

## Weekly meetings
Weekly 15min meetings
Write your time preference below
Online
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Hao | 10-12,17-19 | 17-19 | Anytime | 17-19 | 17-19 | Anytime
Nina | Anytime | 13-19 | Anytime | Anytime | 17-19 | 15-18
Joonas | Anytime (maybe not 16-18) | Anytime | Anytime (maybe not 14-16) | Anytime | Anytime (maybe not 16-18) | Anytime
Erika
Sofia | 13-18 | 13-18 | 13-18 | 13-18 | 13-18 | -
Kaarlo
Tuomo
Binh
Heidi | - | 15-19 | 2023-12-08 | Anytime | 12-16 | -
At campus (or client office)
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Hao |  |  | Anytime |  |  | Anytime
Nina |  |  |  |  | 15-18
Joonas
Erika
Sofia
Kaarlo
Tuomo
Binh
Heidi | - | 15-19 | 8-11:30 | Anytime | 13-16 | -
Scrum events note
Sprint | 3 weeks | Can be more for exam week and holidays
Daily | 2 times / week | 10-15min
Planning | 1 time / sprint | ~1-2h
Retropective | 1 time / sprint | ~45min
Review | 1 time / sprint | ~30min